## List
Table of Contents
PAGE
1 | Monthly Progress | 2
2 | Overall Progress Status | 3
3 | Detail Works Schedule | 4
4 | Fabrication Status | 5
5 | Submittal Document List | 6
6 | Shipping Plan (to be later) | 10
7 | Change Order Status | 11
8 | Issue | 12

## 1. Monthly Progress
1. Monthly Progress | [5 empty] | 2025-08-30
NO. | DESCRIPTION | WEIGHT FACTOR | PROGRESS (%) |  |  | REMARK
|  |  | LAST MONTH | THIS MONTH | ACC.
1 | Catalyst | 37.64% | 3.76% | 0.003643% | 3.764%
2 | Catalyst Structure | 4.705% | 4.47% | 0.2346% | 4.705%
3 | Static Mixer | 0.9409% | 0.24% | -0.004772% | 0.2352%
4 | Ammonia Injection Grid | 7.527% | 1.88% | 0.001822% | 1.882%
5 | Header & Manifold | 0.9409% | 0.09% | 0.004091% | 0.09409%
6 | Dilution Air Fan | 4.705% | 1.18% | -0.003861% | 1.176%
7 | Manual Valve | 1.882% | 0.19% | -0.001818% | 0.1882%
8 | Pipe Support | 0.9409% | 0.09% | 0.004091% | 0.09409%
9 | Piping Spool(Duct) | 0.9409% | 0.09% | 0.004091% | 0.09409%
10 | Raw Material | 4.705% | 0.47% | 0.0004554% | 0.4705%
11 | Panel(MCC, LCP, E.H.T, Chemical) | 11.29% | 1.13% | -0.000907% | 1.129%
12 | Control Valve | 2.823% | 0.28% | 0.002273% | 0.2823%
13 | Control Damper | 1.204% | 0.12% | 0.0004366% | 0.1204%
14 | Instrument | 15.05% | 1.51% | -0.004543% | 1.505%
15 | Miscellaneous(Electric) -Hook Up, Cable, Cable Tray, etc) | 4.705% | 0.47% | 0.0004554% | 0.4705%
TOTAL |  | 100% | 15.97% | 0% | 16.21%
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## 2. Overall Project Progress
| 2. Overall Progress Status | [10 empty] | 2025-08-30
DESCRIPTION |  | 계약금액 | WEIGHT FACTOR | APPLI- CATION | PROCESS | [6 empty] | PROGRESS | REMARK
|  |  |  | A | MATERIAL / PURCHASE ORDER | MATERIAL ORDER | FABRICATION | PAINTING | PACKING | DELIVERY | COMPLETION
|  |  |  | B | MATERIAL / PURCHASE ORDER | MATERIAL ORDER | FABRICATION | PACKING |  | DELIVERY | COMPLETION
[5 empty] | 10% | 15% | 50% | 10% | 10% | 5% | 100%
1. | Catalyst | 400000000 | 37.64% | B | 10% |  |  |  |  | 0% | 10% | 3.764%
2. | Catalyst Structure | 50000000 | 4.705% | A | 10% | 15% | 50% | 10% | 10% | 5% | 100% | 4.705%
3. | Static Mixer | 10000000 | 0.9409% | B | 10% | 15% | 0% | 0% |  |  | 25% | 0.2352%
4. | Ammonia Injection Grid | 80000000 | 7.527% | B | 10% | 15% |  |  |  | 0% | 25% | 1.882%
5. | Header & Manifold | 10000000 | 0.9409% | B | 10% | 0% | 0% | 0% |  |  | 10% | 0.09409%
6. | Dilution Air Fan | 50000000 | 4.705% | A | 10% | 15% | 0% | 0% | 0% |  | 25% | 1.176%
7. | Manual Valve | 20000000 | 1.882% | B | 10% | 0% | 0% | 0% |  | 0% | 10% | 0.1882%
8. | Pipe Support | 10000000 | 0.9409% | A | 10% | 0% | 0% |  |  | 0% | 10% | 0.09409%
9. | Piping Spool(Duct) | 10000000 | 0.9409% | B | 10% | 0% | 0% |  | 0% | 0% | 10% | 0.09409%
10. | Raw Material | 50000000 | 4.705% | A | 10% | 0% | 0% |  |  |  | 10% | 0.4705%
11. | Panel(MCC, LCP, E.H.T, Chemical) | 120000000 | 11.29% | B | 10% | 0% | 0% |  |  |  | 10% | 1.129%
12. | Control Valve | 30000000 | 2.823% | B | 10% | 0% | 0% | 0% | 0% |  | 10% | 0.2823%
13. | Control Damper | 12800000 | 1.204% | B | 10% | 0% | 0% | 0% | 0% |  | 10% | 0.1204%
14. | Instrument | 160000000 | 15.05% | B | 10% | 0% | 0% | 0% | 0% |  | 10% | 1.505%
15. | Miscellaneous(Electric) -Hook Up, Cable, Cable Tray, etc) | 50000000 | 4.705% | A | 10% | 0% | 0% | 0% |  |  | 10% | 0.4705%
TOTAL |  | 1062800000 | 100% |  | 10% | 4.286% | 3.846% | 1.111% | 1.667% | 0.8333% | 19% | 16.21%
1062800000
0

## 3-2 Fabrication time Schedu (hidden)
3.2 Fabrication Time Schedule | [39 empty] | 2015-08-28
No. | ITEM |  |  |  |  | Contract |  |  |  |  | Plan / Actual | Sub-Order Status |  |  |  | Manuf.Ⅰ | [5 empty] | Inspection | [15 empty] | Manuf. Ⅱ |  | Transportation |  |  |  | REMARK
| Main Item | Item | Expediter |  | Unit | Q'ty | Supplier | Manuf. (Location) | Delivery Date | Delivery Condition |  | Procurement |  | Intermediate Transportation |  | Pre - Fab. |  | Machining |  | Welding |  | PMI |  | NDE |  | Hydro Test |  | Leak Test |  | Seat Leak Test |  | Efficiency Test |  | Visual Test |  | Function Test |  | Painting |  | Shipping permits (Packing) |  | Transport to Site
Tag.NO.
[12 empty] | Start | Finish | Start | Finish | Start | Finish | Start | Finish | Start | Finish | Start | Finish | Start | Finish | Start | Finish | Start | Finish | Start | Finish | Start | Finish | Start | Finish | Start | Finish | Start | Finish | Start | Finish | Start | Finish
1 | SCR | CATALYST FRAME AND GAS SEALING DEVICE |  | 51HSD90 BT002 | SET | 2 | BLUE BIRD | KOREA | 2015-10-15 | DDP | P | 2015-04-25 | 2015-05-25 |  |  | 2015-05-19 | 2015-05-26 | 2015-05-26 | 2015-06-03 | 2015-06-04 | 2015-06-27 |  |  | 2015-07-31 | 2015-07-31 | [8 empty] | 2015-08-10 | 2015-08-10 |  |  | 2015-08-10 | 2015-08-10 | 2015-10-10 | 2015-10-13 | 2015-10-15 | 2015-10-15
|  |  |  | 52HSD90 BT002 | [6 empty] | A | 2015-04-20 | 2015-05-20 |  |  | 2015-05-16 | 2015-05-22 | 2015-05-23 | 2015-05-28 | 2015-05-28 | 2015-06-20
2 | SCR | AMMONIA INJECTION GRID (AIG) |  | 51HSG90 AF001 | SET | 2 | BLUE BIRD | KOREA | 2015-10-15 | DDP | P | 2015-04-25 | 2015-05-25 |  |  | 2015-05-19 | 2015-05-26 | 2015-05-26 | 2015-06-03 | 2015-06-04 | 2015-06-27 |  |  | 2015-06-10 | 2015-06-11 | [8 empty] | 2015-07-29 | 2015-07-29 |  |  | 2015-08-03 | 2015-08-03 | 2015-10-10 | 2015-10-13 | 2015-10-15 | 2015-10-15
|  |  |  | 52HSG90 AF001 | [6 empty] | A | 2015-04-20 | 2015-05-20 |  |  | 2015-05-16 | 2015-05-22 | 2015-05-23 | 2015-05-28 | 2015-05-28 | 2015-06-22 |  |  | 2015-06-10 | 2015-06-11 | [8 empty] | 2015-07-29 | 2015-07-29 |  |  | 2015-07-29 | 2015-07-29
3 | SCR | VAPORIZER |  | 51HSG90 AC001 | SET | 2 | BLUE BIRD | KOREA | 2016-01-15 | DDP | P | 2015-04-25 | 2015-06-09 |  |  | 2015-09-10 | 2015-09-14 | 2015-09-15 | 2015-09-19 | 2015-09-20 | 2015-10-04 |  |  | 2015-10-05 | 2015-10-05 |  |  | 2015-10-15 | 2015-10-15 |  |  |  |  | 2015-10-15 | 2015-10-15 |  |  | 2015-10-17 | 2015-10-21 | 2015-12-25 | 2015-12-28 | 2016-01-15 | 2016-01-15
|  |  |  | 52HSG90 AC001 | [6 empty] | A | 2015-04-20 | 2015-06-03
4 | SCR | AMMONIA FLOW CONTROL UNIT (AFCU) |  | 51HSJ90 BN002 | SET | 2 | BLUE BIRD | KOREA | 2016-01-15 | DDP | P | 2015-04-25 | 2015-06-09 |  |  | 2015-09-29 | 2015-10-01 | 2015-10-02 | 2015-10-04 | 2015-10-05 | 2015-10-12 |  |  | 2015-10-13 | 2015-10-13 | [8 empty] | 2015-10-15 | 2015-10-15 |  |  | 2015-10-17 | 2015-10-21 | 2015-12-25 | 2015-12-28 | 2016-01-15 | 2016-01-15
|  |  |  | 52HSJ90 BN002 | [6 empty] | A | 2015-04-20 | 2015-06-03
5 | SCR | OUTER PIPING WITH MANIFOLD |  | 51 HSC90 BR001~002, 51HSG90 BR001~002, 011~022, 031~066 | SET | 2 | BLUE BIRD | KOREA | 2016-01-15 | DDP | P | 2015-04-25 | 2015-06-09 |  |  | 2015-11-20 | 2015-11-24 | 2015-11-25 | 2015-11-30 | 2015-12-01 | 2015-12-12 |  |  | 2015-12-13 | 2015-12-13 | [8 empty] | 2015-12-15 | 2015-12-15 |  |  | 2015-12-17 | 2015-12-23 | 2015-12-25 | 2015-12-28 | 2016-01-15 | 2016-01-15
|  |  |  | 52 HSC90 BR001~002, 52HSG90 BR001~002, 011~022, 031~066 | [6 empty] | A | 2015-04-20 | 2015-06-03
6 | SCR | CATALYST |  | 51HSD90 BT001 | SET | 2 | CERAM | AUSTRIA | 2016-11-30 | DDP | P | 2016-03-01 | 2016-04-30 |  |  | 2016-05-01 | 2016-08-13 | [14 empty] | 2016-08-15 | 2016-08-15 | 2016-08-16 | 2016-08-16 |  |  |  |  | 2016-08-30 | 2016-09-09 | 2016-09-10 | 2016-11-30
|  |  |  | 52HSD90 BT001 | [6 empty] | A
7 | SCR | EXHAUST GAS CIRCULATION FAN |  | 51HSC90 AN001~2 | SET | 4 | SAMWON E & B | KOREA | 2016-01-15 | DDP | P | 2015-04-25 | 2015-05-25 |  |  | 2015-09-14 | 2015-09-16 | 2015-06-17 | 2015-09-19 | 2015-09-20 | 2015-10-04 |  |  | 2015-09-15 | 2015-09-15 | [8 empty] | 2015-10-05 | 2015-10-05 | 2015-10-05 | 2015-10-05 | 2015-10-06 | 2015-10-10 | 2015-12-25 | 2015-12-28 | 2016-01-15 | 2016-01-15
|  |  |  | 52HSC90 AN001~2 | [6 empty] | A | 2015-05-04 | 2015-05-30
8 | SCR | AMMONIA INJECTION NOZZLE |  | 51HSJ90 BN001 | SET | 6 | SPRAY SYS. KOREA | KOREA | 2016-01-15 | DDP | P | 2015-05-15 | 2015-05-30 |  |  | 2015-09-05 | 2015-09-06 | 2015-09-07 | 2015-09-09 | 2015-09-10 | 2015-09-14 | [12 empty] | 2015-09-15 | 2015-09-15 | 2015-09-15 | 2015-09-15 |  |  | 2015-12-25 | 2015-12-28 | 2016-01-15 | 2016-01-15
|  |  |  | 52HSJ90 BN001 | [6 empty] | A | 2015-05-15 | 2015-05-30
9 | SCR | EXPANSION JOINT |  | 51HSG90 AS011~042 | SET | 66 | DMT | KOREA | 2016-01-15 | DDP | P | 2015-10-15 | 2015-11-10 |  |  | 2015-11-11 | 2015-11-15 | 2015-11-16 | 2015-11-19 | 2015-11-20 | 2015-12-04 |  |  | 2015-11-20 | 2015-11-20 |  |  | 2015-12-05 | 2015-12-05 |  |  |  |  | 2015-12-05 | 2015-12-05 |  |  | 2015-12-06 | 2015-12-09 | 2015-12-25 | 2015-12-28 | 2016-01-15 | 2016-01-15
|  |  |  | 52HSG90 AS011~042 | [6 empty] | A
10 | SCR | MANUAL DAMPER |  | 51HSG90 AA001~012 | SET | 24 | BLUE BIRD | KOREA | 2016-01-15 | DDP | P | 2015-11-01 | 2015-11-19 |  |  | 2015-11-20 | 2015-11-24 | 2015-11-25 | 2015-11-30 | 2015-12-01 | 2015-12-14 |  |  | 2015-12-05 | 2015-12-05 |  |  | 2015-12-15 | 2015-12-15 |  |  |  |  | 2015-12-15 | 2015-12-15 |  |  |  |  | 2015-12-25 | 2015-12-28 | 2016-01-15 | 2016-01-15
|  |  |  | 52HSG90 AA001~012 | [6 empty] | A
11 | SCR | MANUAL VALVE (GATE, GLOBE, CHECK) |  | - | SET | 180 | DONG-KANG METAL | KOREA | 2016-01-15 | DDP | P | 2015-05-01 | 2015-05-15 |  |  | 2015-05-18 | 2015-05-20 | 2015-05-21 | 2015-05-29 | 2015-06-01 | 2015-06-12 |  |  | 2015-09-01 | 2015-09-01 | 2015-09-20 | 2015-09-20 | [6 empty] | 2015-09-20 | 2015-09-20 |  |  | 2015-09-15 | 2015-09-15 | 2015-12-25 | 2015-12-28 | 2016-01-15 | 2016-01-15
[11 empty] | A | 2015-05-01 | 2015-05-15 |  |  | 2015-05-18 | 2015-05-20 | 2015-05-21 | 2015-05-29 | 2015-06-01 | 2015-06-30
12 | SCR | MANUAL VALVE (BUTTERFLY) |  | 51HSC90 AA001 | SET | 2 | SEJIN VALVE | KOREA | 2016-01-15 | DDP | P | 2015-05-01 | 2015-05-15 |  |  | 2015-05-18 | 2015-05-20 | 2015-05-21 | 2015-05-29 | 2015-06-01 | 2015-06-12 |  |  |  |  | 2015-09-21 | 2015-09-21 | [6 empty] | 2015-09-21 | 2015-09-21 |  |  | 2015-09-15 | 2015-09-15 | 2015-12-25 | 2015-12-28 | 2016-01-15 | 2016-01-15
|  |  |  | 51HSC90 AA002 | [6 empty] | A | 2015-05-01 | 2015-05-15 |  |  | 2015-05-18 | 2015-05-20 | 2015-05-21 | 2015-05-29 | 2015-06-01 | 2015-06-30
13 | SCR | INSULATION |  | - | SET | 2 | SEWON T&S | KOREA | 2016-01-15 | DDP | P | 2015-10-15 | 2015-11-10 |  |  | 2015-11-11 | 2015-12-16 | [16 empty] | 2015-12-17 | 2015-12-17 |  |  |  |  | 2015-12-25 | 2015-12-28 | 2016-01-15 | 2016-01-15
A
14 | SCR | ANALYZER |  | QYCA 51HSY90 CQ001~004 | SET | 2 | SIEMENS | GERMANY | 2016-01-15 | DDP | P | 2015-04-10 | 2015-07-10 |  |  | 2015-07-10 | 2015-07-20 | [16 empty] | 2015-12-18 | 2015-12-18 | 2015-12-18 | 2015-12-18 |  |  | 2015-12-25 | 2015-12-28 | 2016-01-15 | 2016-01-15
|  |  |  | QYCA 52HSY90 CQ001~004 | [6 empty] | A | 2015-04-14 | 2015-06-24 |  |  | 2015-06-27 | 2015-08-01
15 | SCR | INSTRUMENT (PT, FT, PS) |  | - | SET | 2 | YOKOGAWA, KOREA NAGANO | JAPAN KOREA | 2016-01-15 | DDP | P | 2015-04-20 | 2015-06-15 |  |  | 2015-06-16 | 2015-08-17 | [16 empty] | 2015-08-15 | 2015-08-15 |  |  |  |  | 2015-12-25 | 2015-12-28 | 2016-01-15 | 2016-01-15
|  |  |  | - | [6 empty] | A | 2015-04-29 | 2015-06-15 |  |  | 2015-07-01 | 2015-08-17
16 | SCR | INSTRUMENT (TT, T/C, WELL) |  | - | SET | 2 | SIEMENS, KOREA NAGANO | US KOREA | 2016-01-15 | DDP | P | 2015-06-12 | 2015-07-17 |  |  | 2015-07-18 | 2015-08-14 | [16 empty] | 2015-08-15 | 2015-08-15 |  |  |  |  | 2015-12-25 | 2015-12-28 | 2016-01-15 | 2016-01-15
|  |  |  | - | [6 empty] | A | 2015-06-15 | 2015-07-17 |  |  | 2015-07-01 | 2015-08-14
17 | SCR | INSTRUMENT (PG,TG,WELL) |  | - | SET | 2 | WISE | KOREA | 2016-01-15 | DDP | P | 2015-06-12 | 2015-07-17 |  |  | 2015-07-18 | 2015-08-14 | [16 empty] | 2015-08-15 | 2015-08-15 |  |  |  |  | 2015-12-25 | 2015-12-28 | 2016-01-15 | 2016-01-15
|  |  |  | - | [6 empty] | A | 2015-06-15 | 2015-07-17 |  |  | 2015-07-01 | 2015-08-14
18 | SCR | INSTRUMENT (ORIFICE) |  | FYSA 51HSG90 CH101 | SET | 2 | DAERYUN | KOREA | 2016-01-15 | DDP | P | 2015-06-12 | 2015-07-17 |  |  | 2015-07-18 | 2015-08-14 | [16 empty] | 2015-08-15 | 2015-08-15 |  |  |  |  | 2015-12-25 | 2015-12-28 | 2016-01-15 | 2016-01-15
|  |  |  | FYSA 52HSG90 CH101 | [6 empty] | A | 2015-06-15 | 2015-07-17 |  |  | 2015-07-01 | 2015-08-14
19 | SCR | AMMONIA GAS DETECTOR |  | XE 51HSG90 CQ001 | SET | 2 | GASTRON | KOREA | 2016-01-15 | DDP | P | 2015-06-19 | 2015-07-10 |  |  | 2015-07-11 | 2015-08-20 | [16 empty] | 2015-08-21 | 2015-08-21 | 2015-08-21 | 2015-08-21 |  |  | 2015-12-25 | 2015-12-28 | 2016-01-15 | 2016-01-15
|  |  |  | XE 52HSG90 CQ001 | [6 empty] | A | 2015-06-15 | 2015-06-30 |  |  | 2015-07-01 | 2015-08-14
20 | SCR | FUNCTION VALVE (ON/OFF VALVE) |  | 51HSJ90 AA003, 51HSS90 A005 | SET | 4 | AUTOMA | KOREA | 2016-01-15 | DDP | P | 2015-04-10 | 2015-08-14 |  |  | 2015-06-27 | 2015-08-16 | [8 empty] | 2015-08-17 | 2015-08-17 |  |  | 2015-08-17 | 2015-08-17 |  |  | 2015-08-17 | 2015-08-17 | 2015-08-17 | 2015-08-17 |  |  |  |  | 2016-01-15 | 2016-01-15
|  |  |  | 52HSJ90 AA003, 52HSS90 A005 | [6 empty] | A | 2015-04-14 | 2015-06-26 |  |  | 2015-06-27 | 2015-08-10
21 | SCR | FUNCTION VALVE (FLOW CONTRL VALVE) |  | 51HSJ90 AA101 | SET | 2 | CCI KOREA | KOREA | 2016-01-15 | DDP | P | 2015-04-10 | 2015-08-14 |  |  | 2015-06-27 | 2015-08-17 | [8 empty] | 2015-08-18 | 2015-08-18 |  |  | 2015-08-18 | 2015-08-18 |  |  | 2015-08-18 | 2015-08-18 | 2015-08-18 | 2015-08-18 |  |  |  |  | 2016-01-15 | 2016-01-15
|  |  |  | 52HSJ90 AA101 | [6 empty] | A | 2015-04-14 | 2015-06-26 |  |  | 2015-06-27 | 2015-08-10
22 | SCR | FUNCTION VALVE (PRV) |  | 51HSS90 AA191, 51HSL90 AA191 | SET | 4 | JOKWANG | KOREA | 2016-01-15 | DDP | P | 2015-06-19 | 2015-07-24 |  |  | 2015-06-27 | 2015-08-18 | [8 empty] | 2015-08-19 | 2015-08-19 | [6 empty] | 2015-10-05: 2015-08-19; 2015-10-05: 2015-08-19; 2016-01-15: 2016-01-15; 2016-01-15: 2016-01-15
|  |  |  | 52HSS90 AA191, 52HSL90 AA191 | [6 empty] | A | 2015-06-15 | 2015-06-26 |  |  | 2015-06-27 | 2015-08-10
23 | SCR | PANEL |  | PDP 50HSY00GH001 | SET | 1 | LINE SYSTEM | KOREA | 2016-01-15 | DDP | P | 2015-08-03 | 2015-08-14 |  |  | 2015-08-17 | 2015-09-11 | [16 empty] | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 |  |  | 2015-12-28 | 2015-12-28 | 2016-01-15 | 2016-01-15
|  |  |  | PDP 50HSY00GH002 | [6 empty] | A | 2015-07-01 |  |  |  | 2015-07-01
24 | SCR | JUNCTION BOX |  | 51/52HSY10GZ101 | SET | 1 | LINE SYSTEM | KOREA | 2016-01-15 | DDP | P | 2015-08-03 | 2015-08-14 |  |  | 2015-08-17 | 2015-09-11 | [16 empty] | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 |  |  | 2015-12-28 | 2015-12-28 | 2016-01-15 | 2016-01-15
[11 empty] | A | 2015-07-01 |  |  |  | 2015-07-01
25 | SCR | INSTRUMENT RACK & STANCHION |  |  | SET | 1 | LINE SYSTEM | KOREA | 2016-01-15 | DDP | P | 2015-08-03 | 2015-08-14 |  |  | 2015-08-17 | 2015-09-11 | [16 empty] | 2015-12-10 | 2015-12-10 |  |  |  |  | 2015-12-28 | 2015-12-28 | 2016-01-15 | 2016-01-15
[11 empty] | A | 2015-07-01 |  |  |  | 2015-07-01
26 | SCR | BULK MATERIAL |  | - | SET | 1 | LINE SYSTEM | KOREA | 2016-01-15 | DDP | P | 2015-08-15 | 2015-09-10 | [20 empty] | 2015-12-25: 2015-12-28; 2015-12-28: 2015-12-28; 2016-01-15: 2016-01-15; 2016-01-15: 2016-01-15
|  |  |  | - | [6 empty] | A | 2015-06-15
27 | SCR | CABLE |  | - | SET | 1 | TOMAS CABLE | KOREA | 2016-01-15 | DDP | P | 2015-08-03 | 2015-09-25 | [20 empty] | 2015-12-25: 2015-12-28; 2015-12-28: 2015-12-28; 2016-01-15: 2016-01-15; 2016-01-15: 2016-01-15
|  |  |  | - | [6 empty] | A | 2015-06-15
Formulas:
Delivery Date = [Finish]
NDE = [NDE, row above]
Finish = [Finish, row above]

## 3-2 sheet (hidden)
2015
|  | APRIL | [15 empty] | MAY | [30 empty] | JUNE | [29 empty] | JULY | [30 empty] | AUGUST
|  | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
PLAN | SUM | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| ACC | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
ACTURE | SUM | APRIL 15: 0%; APRIL 16: 0%; APRIL 17: 0%; APRIL 18: 0%; APRIL 19: 0%; APRIL 20: 0.2832%; APRIL 21: 0.2832%; APRIL 22: 0.2832%; APRIL 23: 0.2832%; APRIL 24: 0.2832%; APRIL 25: 0.2832%; APRIL 26: 0.2832%; APRIL 27: 0.2832%; APRIL 28: 0.2832%; APRIL 29: 0.2832%; APRIL 30: 0.2832%; MAY 1: 0.2832%; MAY 2: 0.2832%; MAY 3: 0.2832%; MAY 4: 0.2832%; MAY 5: 0.2832%; MAY 6: 0.2832%; MAY 7: 0.2832%; MAY 8: 0.2832%; MAY 9: 0.2832%; MAY 10: 0.2832%; MAY 11: 0.2832%; MAY 12: 0.2832%; MAY 13: 0.2832%; MAY 14: 0.2832%; MAY 15: 0.2832%; MAY 16: 0.5534%; MAY 17: 0.5534%; MAY 18: 0.5534%; MAY 19: 0.5534%; MAY 20: 0.8312%; MAY 21: 0.6699%; MAY 22: 0.6167%; MAY 23: 0.331%; MAY 24: 0.331%; MAY 25: 0.331%; MAY 26: 0.331%; MAY 27: 0.331%; MAY 28: 1.373%; MAY 29: 1.095%; MAY 30: 1.095%; MAY 31: 1.095%; JUNE 1: 1.095%; JUNE 2: 1.095%; JUNE 3: 1.095%
| ACC | 0% | 0% | 0% | 0% | 0% | 0.2832% | 0.5665% | 0.8497% | 1.133% | 1.416% | 1.699% | 1.983% | 2.266% | 2.549% | 2.832% | 3.116% | 3.399% | 3.682% | 3.965% | 4.249% | 4.532% | 4.815% | 5.098% | 5.382% | 5.665% | 5.948% | 6.231% | 6.515% | 6.798% | 7.081% | 7.364% | 7.918% | 8.471% | 9.024% | 9.578% | 10.41% | 11.08% | 11.7% | 12.03% | 12.36% | 12.69% | 13.02% | 13.35% | 14.72% | 15.82% | 16.91% | 18.01% | 19.1% | 20.2% | 21.29% | 21.29% | 21.29% | 21.29% | 21.29% | 21.29% | 21.29% | 21.29% | 21.29% | 21.29% | 21.29% | 21.29% | 21.29% | 21.29% | 21.29% | 21.29% | 21.29% | 21.29% | 21.29% | 21.29% | 21.29% | 21.29% | 21.29% | 21.29% | 21.29% | 21.29% | 21.29% | 21.29% | 21.29% | 21.29% | 21.29% | 21.29% | 21.29% | 21.29% | 21.29% | 21.29% | 21.29% | 21.29% | 21.29% | 21.29% | 21.29%

## Inspection time Schedule (hidden)
Inspection Time Schedule | [34 empty] | 2015-06-26
No. | Item | Unit | Q'ty | Supplier | Manuf. (Location) | Delivery Date | Delivery Condition | Plan / Actual | FINAL INSPECTION |  |  |  | Manuf.Ⅰ |  |  |  | Inspection | [21 empty] | REMARK
[13 empty] | Pre - Fab. |  | Machining |  | Material |  | Welding |  | NDE |  | Hydro Test |  | Leak Test |  | Seat Leak Test |  | Visual Test |  | Function Test |  | Painting |  | Packing |  | Transport to Site
[17 empty] | R |  | R |  | R |  | W/SW |  | W/SW |  | W/SW |  | W |  | W |  | W/SW |  | W/SW
[9 empty] | Start | Finish | Start | Finish | Start | Finish | Start | Finish |  |  | Start | Finish | Start | Finish | Start | Finish | Start | Finish | Start | Finish | Start | Finish | Start | Finish | Start | Finish | Start | Finish | Start | Finish
1 | CATALYST FRAME AND SEALING | SET | 2 | EMKO | KOREA | 2020-12-15 | DDP | P | 2015-04-25 | 2015-05-25 |  |  | 2015-05-19 | 2015-05-26 | 2015-05-26 | 2015-06-03 | 2020-11-02 | 2020-11-02 | 2020-11-02 | 2020-11-02 | 2020-11-02 | 2020-11-02 | [6 empty] | 2020-11-02 | 2020-11-02 | [6 empty] | 2015-10-15 | 2015-10-15
[8 empty] | A | 2015-04-20 | 2015-05-20 |  |  | 2015-05-19: 2015-05-16; 2015-05-26: 2015-05-22; 2015-05-26: 2015-05-23; 2015-06-03: 2015-05-28
2 | AMMONIA INJECTION GRID | SET | 2 | EMKO | KOREA | 2020-12-15 | DDP | P | 2015-04-25 | 2015-05-25 |  |  | 2015-05-19 | 2015-05-26 | 2015-05-26 | 2015-06-03 |  |  | 2020-11-03 | 2020-11-03 | 2020-11-03 | 2020-11-03 | [6 empty] | 2015-07-29 | 2015-07-29 | [6 empty] | 2015-10-15 | 2015-10-15
[8 empty] | A | 2015-04-20 | 2015-05-20 |  |  | 2015-05-19: 2015-05-16; 2015-05-26: 2015-05-22; 2015-05-26: 2015-05-23; 2015-06-03: 2015-05-28
3 | REDUCING AGENT INJECTION GRID | SET | 2 | EMKO | KOREA | 2020-12-15 | DDP | P |  |  |  |  | 2020-11-02: 2020-11-03; 2020-11-02: 2020-11-03; 2020-11-02: 2020-11-03; 2020-11-02: 2020-11-03
A
4 | VAPORIZER | SET | 2 | EMKO | KOREA | 2020-12-15 | DDP | P | 2015-04-25 | 2015-06-09 |  |  | 2015-09-10 | 2015-09-14 | 2015-09-15 | 2015-09-19 |  |  | 2015-09-20 | 2015-10-04 | 2015-10-05 | 2015-10-05 |  |  | 2015-10-15 | 2015-10-15 |  |  | 2015-10-15 | 2015-10-15 |  |  | 2015-10-17 | 2015-10-21 | 2015-12-25 | 2015-12-28 | 2016-01-15 | 2016-01-15
[8 empty] | A | 2015-04-20 | 2015-06-03
5 | INJECTION NOZZLE | SET | 2 | SPRAY SYS. KOREA | KOREA | 2020-12-15 | DDP | P | 2015-04-25 | 2015-06-09 |  |  | 2015-09-29 | 2015-10-01 | 2015-10-02 | 2015-10-04 |  |  | 2015-10-05 | 2015-10-12 | 2015-10-13 | 2015-10-13 | [6 empty] | 2015-10-15 | 2015-10-15 |  |  | 2015-10-17 | 2015-10-21 | 2015-12-25 | 2015-12-28 | 2016-01-15 | 2016-01-15
[8 empty] | A | 2015-04-20 | 2015-06-03
6 | HOT FLUE GAS FAN | SET | 2 | SAMWON E & B | KOREA | 2020-12-15 | DDP | P
A
7 | COOLING AIR FAN SKID UNIT | SET | 2 | SAMWON E & B | KOREA | 2020-12-15 | DDP | P | 2015-04-25 | 2015-06-09 |  |  | 2015-11-20 | 2015-11-24 | 2015-11-25 | 2015-11-30 |  |  | 2015-12-01 | 2015-12-12 | 2015-12-13 | 2015-12-13 | [6 empty] | 2015-12-15 | 2015-12-15 |  |  | 2015-12-17 | 2015-12-23 | 2015-12-25 | 2015-12-28 | 2016-01-15 | 2016-01-15
[8 empty] | A | 2015-04-20 | 2015-06-03
8 | AMMONIA / RA FLOW CONTROL UNIT | SET | 2 | LATER | LATER | 2020-12-15 | DDP | P | 2016-03-01 | 2016-04-30 |  |  | 2015-05-19: 2016-05-01; 2015-05-26: 2016-08-13 | [6 empty] | 2016-08-16 | 2016-08-16 |  |  |  |  | 2016-08-30 | 2016-09-09 | 2016-09-10 | 2016-11-30
A
9 | DIRECT INJECTION YPES SKID UNIT | SET | 6 | SPRAY SYS. KOREA | KOREA | 2020-12-15 | DDP | P | 2015-05-15 | 2015-05-30 |  |  | 2015-09-05 | 2015-09-06 | 2015-09-07 | 2015-09-09 |  |  | 2015-09-10 | 2015-09-14 | [8 empty] | 2015-09-15 | 2015-09-15 | 2015-09-15 | 2015-09-15 |  |  | 2015-12-25 | 2015-12-28 | 2016-01-15 | 2016-01-15
[8 empty] | A | 2015-05-15 | 2015-05-30
10 | CONTROL / MANUAL VALVE |  |  |  |  | 2020-12-15 | DDP | P
A
11 | PRESSURE SAFETY/REGULATING VALVE | SET | 66 | DMT | KOREA | 2020-12-15 | DDP | P | 2015-10-15 | 2015-11-10 |  |  | 2015-11-11 | 2015-11-15 | 2015-11-16 | 2015-11-19 |  |  | 2015-11-20 | 2015-12-04 | 2015-11-20 | 2015-11-20 |  |  | 2015-12-05 | 2015-12-05 |  |  | 2015-12-05 | 2015-12-05 |  |  | 2015-12-06 | 2015-12-09 | 2015-12-25 | 2015-12-28 | 2016-01-15 | 2016-01-15
A
12 | MANUAL/PNEUMATIC DAMPER | SET | 2 | LATER | LATER | 2020-12-15 | DDP | P | 2015-05-01 | 2015-05-15 |  |  | 2015-05-18 | 2015-05-20 | 2015-05-21 | 2015-05-29 |  |  | 2015-06-01 | 2015-06-12 |  |  | 2015-09-21 | 2015-09-21 |  |  |  |  | 2015-09-21 | 2015-09-21 |  |  | 2015-09-15 | 2015-09-15 | 2015-12-25 | 2015-12-28 | 2016-01-15 | 2016-01-15
[8 empty] | A | 2015-05-01 | 2015-05-15 |  |  | 2015-05-18 | 2015-05-20 | 2015-05-21 | 2015-05-29 |  |  | 2015-06-01 | 2015-06-30
13 | PIPING PARTS (RAW MATERILA) & PIPE SUPPORT | SET | 2 | LATER | LATER | 2020-12-15 | DDP | P | 2015-04-10 | 2015-07-10 |  |  | 2015-05-19: 2015-07-10; 2015-05-26: 2015-07-20 | [6 empty] | 2015-12-18 | 2015-12-18 | 2015-12-18 | 2015-12-18 |  |  | 2015-12-25 | 2015-12-28 | 2016-01-15 | 2016-01-15
[8 empty] | A | 2015-04-14 | 2015-06-24 |  |  | 2015-05-19: 2015-06-27; 2015-05-26: 2015-08-01
14 | MANIFOLD FOR AIG/RAIG | SET | 2 | LATER | LATER | 2020-12-15 | DDP | P | 2015-06-12 | 2015-07-17 |  |  | 2015-05-19: 2015-07-18; 2015-05-26: 2015-08-14 | [6 empty] | 2015-08-15 | 2015-08-15 |  |  |  |  | 2015-12-25 | 2015-12-28 | 2016-01-15 | 2016-01-15
[8 empty] | A | 2015-06-15 | 2015-07-17 |  |  | 2015-05-19: 2015-07-01; 2015-05-26: 2015-08-14
15 | WATER SPRAY SYSTEM | SET | 2 | LATER | LATER | 2020-12-15 | DDP | P | 2015-06-12 | 2015-07-17 |  |  | 2015-05-19: 2015-07-18; 2015-05-26: 2015-08-14 | [6 empty] | 2015-08-15 | 2015-08-15 |  |  |  |  | 2015-12-25 | 2015-12-28 | 2016-01-15 | 2016-01-15
[8 empty] | A | 2015-06-15 | 2015-07-17 |  |  | 2015-05-19: 2015-07-01; 2015-05-26: 2015-08-14
16 | INSULATION MATERIAL | SET | 2 | LATER | LATER | 2020-12-15 | DDP | P | 2015-06-19 | 2015-07-10 |  |  | 2015-05-19: 2015-07-11; 2015-05-26: 2015-08-20 | [6 empty] | 2015-08-21 | 2015-08-21 | 2015-08-21 | 2015-08-21 |  |  | 2015-12-25 | 2015-12-28 | 2016-01-15 | 2016-01-15
[8 empty] | A | 2015-06-15 | 2015-06-30 |  |  | 2015-05-19: 2015-07-01; 2015-05-26: 2015-08-14
17 | EMERGENCY SHOWER & EYE WASHER | SET | 2 | LATER | LATER | 2020-12-15 | DDP | P | 2015-04-10 | 2015-08-14 |  |  | 2015-05-19: 2015-06-27; 2015-05-26: 2015-08-17 | 2015-08-18 | 2015-08-18 |  |  | 2015-08-18 | 2015-08-18 | 2015-08-18 | 2015-08-18 | 2015-08-18 | 2015-08-18 |  |  |  |  | 2016-01-15 | 2016-01-15
[8 empty] | A | 2015-04-14 | 2015-06-26 |  |  | 2015-05-19: 2015-06-27; 2015-05-26: 2015-08-10
18 | PLC PANEL | SET | 4 | LATER | LATER | 2020-12-15 | DDP | P | 2015-06-19 | 2015-07-24 |  |  | 2015-05-19: 2015-06-27; 2015-05-26: 2015-08-18 | 2015-08-19 | 2015-08-19 |  |  |  |  | 2015-08-19 | 2015-08-19 | [6 empty] | 2016-01-15 | 2016-01-15
[8 empty] | A | 2015-06-15 | 2015-06-26 |  |  | 2015-05-19: 2015-06-27; 2015-05-26: 2015-08-10
19 | HOOK-UP, CABLE, CALBE TRAY, CONDUIT, HEAT TRACING, LIGHTING AND ETC. | SET | 1 | EWHA Electric Inc. | KOREA | 2020-12-15 | DDP | P | 2015-08-03 | 2015-08-14 |  |  | 2015-05-19: 2015-08-17; 2015-05-26: 2015-09-11 | [6 empty] | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 |  |  | 2015-12-28 | 2015-12-28 | 2016-01-15 | 2016-01-15
[8 empty] | A | 2015-07-01 |  |  |  | 2015-05-19: 2015-07-01
20 | TRANSMITTER (PRESSURE, TEMPERATURE,FLOW) | SET | 1 | ABB KOREA | KOREA | 2020-12-15 | DDP | P | 2015-08-03 | 2015-08-14 |  |  | 2015-05-19: 2015-08-17; 2015-05-26: 2015-09-11 | [6 empty] | 2015-12-10 | 2015-12-10 |  |  |  |  | 2015-12-28 | 2015-12-28 | 2016-01-15 | 2016-01-15
[8 empty] | A | 2015-07-01 |  |  |  | 2015-05-19: 2015-07-01
21 | INDICATOR (PRESSURE,TEMPERATURE THERMOCOUPLE, RTDTHERMOWELL, AIR FILTER,ORIFICE PLATE) | SET | 1 | WISE | KOREA | 2020-12-15 | DDP | P | 2015-08-15 | 2015-09-10 | [24 empty] | 2015-12-28 | 2015-12-28 | 2016-01-15 | 2016-01-15
[8 empty] | A | 2015-06-15
22 | GAS ANALYZER | SET | 1 | Woori Environmental Technology | KOREA | 2020-12-15 | DDP | P | 2015-08-03 | 2015-09-25 | [24 empty] | 2015-12-28 | 2015-12-28 | 2016-01-15 | 2016-01-15
[8 empty] | A | 2015-06-15
23 | Rupture Disc | SET | 1 | LATER | KOREA | 2020-12-15 | DDP | P | 2015-08-03 | 2015-09-25 | [24 empty] | 2015-12-28 | 2015-12-28 | 2016-01-15 | 2016-01-15
[8 empty] | A | 2015-06-15

## 3. Detail Works Schedule
DOC. NO. |  | - |  |  |  | WORKS SCHEDULE
PJT.NAME |  | WAKAYAMA
CUSTOMER |  | BHI
FACILITY |  | SCR SYSTEM | [28 empty] | A | 2025. 08. 30
DATE |  | 2025. 08. .30 | [28 empty] | REV. | DATE |  |  | DESCRIPTION |  | REMARK
NO. | PART NAME |  | DESCRIPTION |  |  | Month | 2024. 04 |  |  | 2024. 05~10 |  |  | 2024. 11 ~ 2025. 05 |  |  | 2025. 06 |  |  | 2025. 07 |  |  | 2025. 08 |  |  | 2025. 09 |  |  | 2025. 10 |  |  | 2025. 11 |  |  | 2025. 12 |  |  | 공정율 (%) | REMARK
[6 empty] | Week | 10 | 20 | 30 | - | - | - | - | - | - | 10 | 20 | 30 | 10 | 20 | 30 | 10 | 20 | 30 | 10 | 20 | 30 | 10 | 20 | 30 | 10 | 20 | 30 | 10 | 20 | 30
A | KEY PLAN |  | MILE STONE
B | ENGINEERING |  | 1) Document | PLAN | 10% | 1 Lot |  | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | [21 empty] | 10%
|  |  |  | ACTUAL |  | 1 Lot |  | 1 | 1 | 1 | 1 | 2 | [24 empty] | 6%
|  |  | 2) Drawing | PLAN | 10% | 1 Lot |  | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | [21 empty] | 10%
|  |  |  | ACTUAL |  | 1 Lot |  | 1 | 1 | 1 | 1 | 2 | [24 empty] | 6%
[Mechanical] | [26 empty] | 0.15
C | HRSG #11 |  | Catalyst | PLAN | 23% | 1 Lot |  |  |  | 1 |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 23%
|  |  |  | ACTUAL |  | 1 Lot | [6 empty] | 2 | [23 empty] | 2%
|  |  | Catalyst Structure | PLAN | 5% | 1 Lot |  |  |  | 0.3 | 0.3 | 0.3 | [10 empty] | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.2 | 5%
|  |  |  | ACTUAL |  | 1 Lot | [7 empty] | 1.2 | 1.2 | [21 empty] | 2.4%
|  |  | Static Mixer | PLAN | 3% | 1 Lot |  |  |  | 0.2 | 0.2 | 0.2 | [12 empty] | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 3%
|  |  |  | ACTUAL |  | 1 Lot | [30 empty] | 0%
|  |  | Ammonia Injection Grid | PLAN | 8% | 1 Lot |  |  |  | 0.5 | 0.5 | 0.5 | [10 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.5 | 8%
|  |  |  | ACTUAL |  | 1 Lot | [7 empty] | 1.2 | 1.2 | [21 empty] | 2.4%
|  |  | Header & Manifold | PLAN | 3% | 1 Lot |  |  |  | 0.2 | 0.2 | 0.2 | [12 empty] | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 3%
|  |  |  | ACTUAL |  | 1 Lot | [30 empty] | 0%
|  |  | Dilution Air Fan | PLAN | 5% | 1 Lot |  |  |  | 0.2 | 0.2 | 0.2 |  |  |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.4 | 0.2 | 0.2 | 0.2 | 5%
|  |  |  | ACTUAL |  | 1 Lot | [6 empty] | 1.8 | 1.8 | 1.2 | 0.2 | 0.2 | 0.2 | [18 empty] | 5.4%
|  |  | Manual Valve | PLAN | 2% | 1 Lot |  |  |  | 0.1 | 0.1 | 0.1 | [9 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.2 | 0.2 | 0.1 | 0.1 | 2%
|  |  |  | ACTUAL |  | 1 Lot | [30 empty] | 0%
|  |  | Pipe Support | PLAN | 5% | 1 Lot |  |  |  | 0.4 | 0.4 | 0.4 | [14 empty] | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.3 | 0.3 | 5%
|  |  |  | ACTUAL |  | 1 Lot | [30 empty] | 0%
|  |  | Piping Spool(Duct) | PLAN | 3% | 1 Lot |  |  |  | 0.2 | 0.2 | 0.2 | [14 empty] | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.3 | 0.3 | 0.3 | 0.3 | 0.2 | 3%
|  |  |  | ACTUAL |  | 1 Lot | [30 empty] | 0%
|  |  | Raw Material | PLAN | 2% | 1 Lot |  |  |  | 0.15 | 0.15 | 0.15 | [14 empty] | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.1 | 0.2 | 0.2 | 2%
|  |  |  | ACTUAL |  | 1 Lot | [30 empty] | 0%
[I&C]
D | HRSG #11 |  | Panel(MCC, LCP, E.H.T, Chemical) | PLAN | 8% | 1 Lot |  |  |  | 0.4 | 0.4 | 0.4 | [9 empty] | 0.4 | 0.4 | 0.4 | 0.4 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.4 | 0.4 | 0.4 | 8%
|  |  |  | ACTUAL |  | 1 Lot | [30 empty] | 0%
|  |  | Control Valve | PLAN | 3% | 1 Lot |  |  |  | 0.15 | 0.15 | 0.15 | [6 empty] | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.1 | 0.1 | 0.1 | 3%
|  |  |  | ACTUAL |  | 1 Lot | [30 empty] | 0%
|  |  | Control Damper | PLAN | 3% | 1 Lot |  |  |  | 0.15 | 0.15 | 0.15 | [6 empty] | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.1 | 0.1 | 0.1 | 3%
|  |  |  | ACTUAL |  | 1 Lot | [30 empty] | 0%
|  |  | Instrument | PLAN | 5% | 1 Lot |  |  |  | 0.2 | 0.2 | 0.2 | [6 empty] | 0.2 | 0.2 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 5%
|  |  |  | ACTUAL |  | 1 Lot | [30 empty] | 0%
|  |  | Miscellaneous(Electric) -Hook Up, Cable, Cable Tray, etc) | PLAN | 2% | 1 Lot |  |  |  | 0.15 | 0.15 | 0.15 | [14 empty] | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.2 | 0.2 | 0.15 | 0.1 | 2%
|  |  |  | ACTUAL |  | 1 Lot | [30 empty] | 0%
PLAN |  |  | Official Rate |  | 100% |  | 0 | 2 | 2 | 2 | 2 | 4 | 3.8 | 4.2 | 3.6 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Accumulated |  | % |  | 0 | 2 | 4 | 6 | 8 | 12 | 15.8 | 20 | 23.6 | 23.8 | 24 | 24.2 | 24.2 | 24.2 | 24.2 | 24.2 | 24.2 | 24.2 | 24.2 | 24.2 | 24.2 | 24.2 | 24.2 | 24.2 | 24.2 | 24.2 | 24.2 | 24.2 | 24.2 | 24.2
ACTUAL |  |  | Official Rate |  | 100% |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 100%
|  |  | Accumulated |  | % |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[ LEGEND ] |  | BD : Basic Design |  |  |  | TR : Transport | [24 empty] | KOM : Kick-Off Meeting
|  | DD : Detail Design |  |  |  | MP : Material Purchasing | [24 empty] | VS : Vendor Selection
|  | FA : For Approval |  |  |  | MFG : Manufacturing | [24 empty] | RFQ : Request for Quotation
|  | FC : For Construction |  |  |  | IN : Inspection | [24 empty] | VP : Vendor Print
100%
[31 empty] | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13
[25 empty] | 0.25 | 0.25 | 0.25 | 0.25 | 0.25
[25 empty] | 0.125 | 0.125 | 0.125 | 0.125 | 0.125 | 0.125 | 0.125 | 0.125 | 0.125 | 0.125 | 0.125 | 0.125
[31 empty] | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15
[34 empty] | 0.1 | 0.1 | 0.1
[22 empty] | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3
[22 empty] | 0.3 | 0.3 | 0.3
[22 empty] | 0.25 | 0.25 | 0.25 | 0.25
[22 empty] | 0.25 | 0.25 | 0.25
[23 empty] | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 |  |  |  | 0.2 | 0.2
[23 empty] | 0.15 | 0.15
[23 empty] | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 |  |  |  | 0.2 | 0.2
[23 empty] | 0.15 | 0.15
[26 empty] | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.1 | 0.1
[25 empty] | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | [5 empty] | 0.15 | 0.15
[22 empty] | 0.15 | 0.15 | 0.15
[22 empty] | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 0.16 | 0.16 | 0.16 | 0.16
[22 empty] | 0.16 | 0.16 | 0.16
[26 empty] | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.1
[26 empty] | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.1 | 0.1
[26 empty] | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.1 | 0.1
[26 empty] | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.1 | 0.1
[26 empty] | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 0.19 | 0.19
[26 empty] | 0.16 | 0.16 | 0.16 | 0.16 | 0.17 | 0.17
[26 empty] | 0.16 | 0.16 | 0.16 | 0.16 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17
[26 empty] | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17 | 0.17
[26 empty] | 0.27 | 0.27 | 0.27 | 0.27 | 0.27 | 0.27 | 0.27
[26 empty] | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 | 0.5 | 0.5
[26 empty] | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.2 | 0.2
[26 empty] | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.2 | 0.2
[26 empty] | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.09 | 0.1 | 0.1
[26 empty] | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13 | 0.13
RFQ/VS/MP/MFG / IN / TR
BD,DD
FA, FC
FA, FC
FA, FC
FA, FC
IN
TR
VS
RFQ
MP
MFG
VS
RFQ
MP
VS
RFQ
MP
VS
RFQ
MP
VS
RFQ
MP
VS
RFQ
VS
RFQ
MP
VS
RFQ
MP
VS
RFQ
MP
VS
RFQ
VS
RFQ
MP
VS
RFQ
MP
VS
RFQ
MP
VS
RFQ
MP
MFG
VS
RFQ
VS
RFQ
MP
VS
RFQ
MP
VS
RFQ
MFG
MP
VS
RFQ
MP
VS
RFQ
VS
RFQ
VS
RFQ
MP
VS
RFQ
VS
RFQ
MP
VS
RFQ
VS
RFQ
MP
RFQ
RFQ
RFQ
RFQ
RFQ
RFQ
RFQ
RFQ
VS
VS
VS
VS
RFQ
VS
RFQ
RFQ
RFQ
RFQ
RFQ
VS
MP
MP
VS
MP
RFQ
RFQ
VS
RFQ
VS
RFQ
VS
RFQ
VS
VS
VS
RFQ
VS
RFQ
VS
RFQ
VS
RFQ
VS
VS
VS
VS
VS
VS
MFG
MFG
VS
VS
RFQ
VS
MP
RFQ, VS
RFQ, VS
RFQ, VS
RFQ, VS
RFQ, VS
RFQ, VS
RFQ, VS
RFQ, VS
RFQ, VS
RFQ, VS
RFQ, VS
RFQ, VS
RFQ, VS
RFQ, VS
MFG
IN
TR
MP
MFG
IN
TR
MP
MFG
IN
TR
MP
MFG
IN
TR
MP
MFG
IN
TR
MP
MFG
IN
TR
MP
MFG
IN
TR
MP
MFG
IN
TR
MP
IN
TR
MP
MFG
IN
TR
MP
MFG
IN
MP
IN
MP
TR
TR
RFQ, VS
IN
TR
MP
MFG
RFQ, VS
RFQ, VS
RFQ, VS
RFQ, VS
RFQ, VS
RFQ, VS
RFQ, VS
RFQ, VS
RFQ, VS
RFQ, VS
RFQ, VS
RFQ, VS
RFQ, VS
RFQ, VS
RFQ, VS
MP
MP
MP
MFG
MFG
IN, TR
IN, TR

## 4. Fabrication Status
4. Fabrication Status | [12 empty] | 2025-08-30
S/N | Description | QTY | PLAN | PO | Manufacturer | P.O status |  | Manufacturing |  |  | Delivery date | Location | Remark
|  |  | ACTUAL |  |  | RFQ | P.O | Start | Finish | Progress (%)
1 | Catalyst | 1 | P |  | CERAM | 2024-05-01 | 2024-10.30 | 2025-06-01 | 2025-10.30 |  | LATER | 오스트리아
|  |  | A |  |  | 2024-05-01 | 2024-11-26
2 | Catalyst Structure | 1 | P |  | EASY S&A | 2024-05-01 | 2024-10.30 | 2025-06-01 | 2025-07-30 | 100% | 2025-08-30 | 충남 당진 | 납품완료
|  |  | A |  |  | 2025-05-01 | 2025-06-01 | 2025-06-25 | 2025-07-30
3 | Static Mixer | 1 | P |  | 삼화제작소 | 2024-05-01 | 2024-10.30 | 2025-10-11 | 2025-11-30 |  | 2025-12-31 | 인천 남동구
|  |  | A |  |  | 2024-05-01 | 2024-11-12
4 | Ammonia Injection Grid | 1 | P |  | ES-Solution | 2024-05-01 | 2024-10.30 |  |  |  | 2025-08-30 | 경기 용인 | 설계 승인 즉시 일정 확정 (EMKO 자체운송, 승인일로부터 15일 예상)
|  |  | A |  |  | 2025-01-15 | 2025-02-20
5 | Header & Manifold | 1 | P |  | ES-Solution | 2024-05-01 | 2024-10.30 | 2025-10-01 | 2025-11-30 |  | 2025-12-31 | 경기 용인
|  |  | A |  |  | 2025-01-15 | 2025-02-20
6 | Dilution Air Fan | 1 | P |  | 동양 | 2024-05-01 | 2024-10.30 | 2025-09-01 | 2025-11-30 |  | 2025-12-31 | 충남 예산
|  |  | A |  |  | 2024-06-03 | 2024-06-26
7 | Manual Valve | 1 | P |  | 동광밸브 | 2024-05-01 | 2024-10.30 | 2025-10-01 | 2025-11-30 |  | 2025-12-31 | 부산
|  |  | A |  |  | 2025-03-01 | 2025-05-01
8 | Pipe Support | 1 | P |  | ES-Solution | 2024-05-01 | 2024-10.30 | 2025-10-21 | 2025-11-30 |  | 2025-12-31 | 경기 용인
|  |  | A |  |  | 2025-01-15 | 2025-02-20
9 | Piping Spool(Duct) | 1 | P |  | ES-Solution | 2024-05-01 | 2024-10.30 | 2025-10-21 | 2025-11-30 |  | 2025-12-31 | 경기 용인
|  |  | A |  |  | 2025-01-15 | 2025-02-20
10 | Raw Material | 1 | P |  | ES-Solution | 2024-05-01 | 2024-10.30 | 2025-09-21 | 2025-11-30 |  | 2025-12-31 | 경기 용인
|  |  | A |  |  | 2025-01-15 | 2025-02-20
11 | Panel(MCC, LCP, E.H.T, Chemical) | 1 | P |  | 이화전기 | 2024-05-01 | 2024-10.30 | 2025-10-01 | 2025-11-30 |  | 2025-12-31 | 경기 안산
|  |  | A |  |  | 2025-02-10 | 2025-02-28
12 | Control Valve | 1 | P |  | KOSO | 2024-05-01 | 2024-10.30 | 2025-09-01 | 2025-11-30 |  | 2025-12-31 | LATER
|  |  | A |  |  | 2025-03-01 | 2025-05-01
13 | Control Damper | 1 | P |  | 오토마 | 2024-05-01 | 2024-10.30 | 2025-09-01 | 2025-11-30 |  | 2025-12-31 | 경기 부천
|  |  | A |  |  | 2025-03-01 | 2025-05-01
14 | Instrument | 1 | P |  | 주영씨엔에스 | 2024-05-01 | 2024-10.30 | 2025-07-01 | 2025-11-30 |  | 2025-12-31 | 경기 부천
|  |  | A |  |  | 2025-03-01 | 2025-05-01
15 | Miscellaneous(Electric) -Hook Up, Cable, Cable Tray, etc) | 1 | P |  | 이화전기 | 2024-05-01 | 2024-10.30 | 2025-09-21 | 2025-11-30 |  | 2025-12-31 | 경기 안산
|  |  | A |  |  | 2025-02-10 | 2025-02-28

## 4. Submittal Document List (hidden)
4. Submittal Document List
PROJECT : GS Dangjin 4 CCPP
ABBREVIATIONS : |  | *Issue Purpose FI : For Information / FA : For Approval / FC : For Construction / FF : For Final / AB : As-Built
* Return Status AP : Approved / AC : Approved as Commented / RE : Resubmit / RJ : Reject
|  | * Code S : Submitted document to SIEMENS | [48 empty] | As of : 2015-08-28
No. | Code | Document Title | Document No. |  |  |  |  | Issue Purpose | Plan |  | 1st Issue |  |  |  | 2nd Issue |  |  |  | 3rd Issue |  |  |  | 4th Issue |  |  |  | 5th Issue |  |  |  | 6th Issue |  |  |  | 7th Issue |  |  |  | 8th Issue |  |  |  | 9th Issue |  |  |  | 10th Issue |  |  |  | Remarks
|  |  | Project code | KKS | DCC | Register | UNID |  | Preliminary | Final | Issued | Rev. | Returned | Result | Issued | Rev. | Returned | Result | Issued | Rev. | Returned | Result | Issued | Rev. | Returned | Result | Issued | Rev. | Returned | Result | Issued | Rev. | Returned | Result | Issued | Rev. | Returned | Result | Issued | Rev. | Returned | Result | Issued | Rev. | Returned | Result | Issued | Rev. | Returned | Result
1 |  | Technical Data & Specification | [49 empty] | FA/FI (80%) | FC (10%) | As-Built (10%) | Total (100%)
1.1 | S | Design report for SCR system | KR1020 | 00HSJ | &MDB080 | 217140 | 445329728 | FA | - | 2014-09-26 | 2014-09-26 | A |  |  | 2014-10-21 | B | [35 empty] | 80% |  |  | 80%
1.2 | S | Special storage requirement for SCR system | KR1020 | 00HSJ | &MDC060 | 217150 | 445330526 | FA | - | 2014-11-17 | 2014-11-17 | A | [39 empty] | 80% |  |  | 80%
1.3 | S | Catalyst module exchange procedure | KR1020 | 00HSJ | &MDC090 | 217170 | 445330533 | FA | - | 2014-11-17 | 2014-11-17 | A |  |  | 2015-03-31 | B |  |  | 2015-08-04 | C | [31 empty] | 80% |  |  | 80%
1.4 | S | System description of HRSG SCR system | KR1020 | 00HSJ | &MFB030 | 217190 | 445330564 | FA | - | 2014-10-15 | 2014-10-15 | A |  |  | 2014-11-12 | B |  |  | 2015-08-06 | C | [31 empty] | 80% |  |  | 80%
1.5 | S | Erection Procedure for SCR system | KR1020 | 00HSJ | &BBC010 | 140901 |  | FA | 2015-01-02 | 2015-02-10 | 2015-02-03 | A | [38 empty] | for SIEMENS erection procedure schedule | 80% |  |  | 80%
1.6 | S | Explosion and fire protection realization concept | KR1020 | 00HSJ | &BBC010 | 140902 |  |  | Not applicable | [42 empty] | 80% |  |  | 80%
1.7 |  | Equipment Data Sheet of Catalyst for SCR system | KR1020 | 00HSJ | &BBC010 | 140903 |  | FA | - | 2014-11-28 | 2015-01-23 | A |  |  | 2015-04-23 | B | [35 empty] | 80% |  |  | 80%
1.8 |  | Equipment Data Sheet of Exhaust Gas Circulation Fan for SCR system | KR1020 | 00HSJ | &BBC010 | 140904 |  | FA | - | 2014-11-28 | 2015-01-23 | A |  |  | 2015-02-27 | B |  |  | 2015-03-20 | C |  |  | 2015-04-15 | D |  |  | 2015-05-29 | E |  |  | 2015-08-25 | F | [19 empty] | 80% |  |  | 80%
1.9 |  | Sub-Vendor List for SCR system | KR1020 | 00HSJ | &BBC010 | 140905 |  | FA | - | 2014-09-26 | 2014-09-26 | A |  |  | 2014-12-26 | B |  |  | 2015-04-30 | C | [31 empty] | 80% |  |  | 80%
1.1 |  | Utility & Power consumption list for SCR system | KR1020 | 00HSJ | &BBC010 | 140906 |  | FA | 2014-10-06 | 2014-12-02 | 2014-12-26 | A |  |  | 2015-03-16 | B | [34 empty] | for SIEMENS consumption list schedule | 80% |  |  | 80%
1.11 |  | Terminal point list & drawing for SCR system | KR1020 | 00HSJ | &BBC010 | 140907 |  | FA | - | 2014-11-17 | 2014-11-17 | A |  |  | 2015-03-16 | B |  |  | 2015-04-23 | C |  |  | 2015-06-05 | D |  |  | 2015-06-15 | E |  |  | 2015-07-15 | F |  |  | 2015-07-24 | G | [15 empty] | 80% |  |  | 80%
1.12 |  | CFD analysis report for SCR system | KR1020 | 00HSJ | &BBC010 | 140908 |  | FA | - | 2014-12-31 | 2015-01-27 | A |  |  | 2015-06-19 | B |  |  | 2015-07-06 | C |  |  | 2015-08-11 | D | [27 empty] | 80% |  |  | 80%
1.13 |  | Erection and Comm. Spare parts list for SCR system | KR1020 | 00HSJ | &BBC010 | 140909 |  | FA | - | 2014-10-15 | 2014-10-15 | A | [39 empty] | 80% |  |  | 80%
1.14 |  | 2 years spare parts list for SCR system | KR1020 | 00HSJ | &BBC010 | 140910 |  | FA | - | 2014-12-19 | 2014-12-19 | A | [39 empty] | 80% |  |  | 80%
1.15 |  | Special Tool List for SCR system | KR1020 | 00HSJ | &BBC010 | 140911 |  | FA | - | 2014-10-15 | 2014-10-15 | A | [39 empty] | 80% |  |  | 80%
1.16 |  | Lubricant list for SCR system | KR1020 | 00HSJ | &BBC010 | 140912 |  | FA | - | 2014-11-17 | 2014-11-17 | A | [39 empty] | 80% |  |  | 80%
1.17 |  | Piping Material Classifications for SCR system | KR1020 | 00HSJ | &BBC010 | 140913 |  | FA | - | 2014-11-28 | 2014-11-28 | A |  |  | 2014-12-19 | B |  |  | 2015-03-09 | C |  |  | 2015-03-17 | D |  |  | 2015-05-07 | E |  |  | 2015-05-18 | F |  |  | 2015-06-05 | G |  |  | 2015-07-15 | H |  |  | 2015-07-24 | I | [7 empty] | 80% |  |  | 80%
1.18 |  | Manual valve list for SCR system | KR1020 | 00HSJ | &BBC010 | 140914 |  | FA | - | 2014-11-28 | 2014-11-28 | A |  |  | 2014-12-19 | B |  |  | 2015-03-18 | C |  |  | 2015-05-08 | D |  |  | 2015-06-05 | E | [23 empty] | 80% |  |  | 80%
1.19 |  | Piping list for SCR system | KR1020 | 00HSJ | &BBC010 | 140915 |  | FA | - | 2014-11-28 | 2014-11-28 | A |  |  | 2014-12-19 | B |  |  | 2015-03-17 | C |  |  | 2015-05-08 | D |  |  | 2015-06-05 | E | [23 empty] | 80% |  |  | 80%
1.2 |  | Heat and mass balance diagram for SCR system | KR1020 | 00HSJ | &BBC010 | 140916 |  | FA | - | 2014-10-30 | 2014-10-30 | A | [39 empty] | 80% |  |  | 80%
1.21 |  | Operating procedure for SCR system | KR1020 | 00HSJ | &BBC010 | 140917 |  | FA | - | 2014-12-19 | 2015-03-16 | A | [39 empty] | 80% |  |  | 80%
1.22 |  | Performance test procedure with correction curve for SCR system | KR1020 | 00HSJ | &BBC010 | 140918 |  | FA | - | 2015-06-30 | [41 empty] | 0% |  |  | 0%
1.23 |  | Commissioning procedure for SCR system | KR1020 | 00HSJ | &BBC010 | 140919 |  | FA | - | 2015-06-30 | [41 empty] | 0% |  |  | 0%
1.24 |  | Operating and Maintenance manual for SCR system | KR1020 | 00HSJ | &BBC010 | 140920 |  | FA | - | 2015-06-15 | [40 empty] | for SIEMENS schedule | 0% |  |  | 0%
1.25 |  | Instruction for Training for SCR system | KR1020 | 00HSJ | &BBC010 | 140921 |  | FA | - | 2015-06-15 | [41 empty] | 0% |  |  | 0%
2 |  | Drawing
2.1 | S | P&ID for SCR system
2.1.1 | S | Symbol and legends | KR1020 | 00HSJ | &MFB030 | 217180 | 445330540 | FA | - | 2014-10-15 | 2014-10-27 | A |  |  | 2015-03-06 | B |  |  | 2015-04-01 | C | [31 empty] | 80% |  |  | 80%
2.1 | S | P&ID of HRSG SCR system | KR1020 | 00HSJ | &MFB030 | 217181 | 445330557 | FA | - | 2014-10-15 | 2015-06-03 | -09 |  |  | 2015-08-11 | -10 | [35 empty] | 80% |  |  | 80%
2.2 | S | Foundation load data for SCR System | KR1020 | 00HSJ | &CLC010 | 217120 | 445330496 | FA | 2014-09-26 | 2014-10-21 | 2014-09-26 | 0 |  |  | 2014-10-21 | A |  |  | 2014-10-30 | B |  |  | 2015-03-02 | C |  |  | 2015-03-18 | D |  |  | 2015-06-10 | E |  |  | 2015-06-12 | F |  |  | 2015-06-25 | G |  |  | 2015-08-18 | H | [7 empty] | 80% |  |  | 80%
2.3 | S | Embedded material for SCR system | KR1020 | 00HSJ | &CLC061 | 217130 | 445330502 | FA | 2014-09-26 | 2014-10-21 | 2014-09-26 | 0 |  |  | 2014-10-21 | A |  |  | 2015-01-23 | B |  |  | 2015-02-27 | C |  |  | 2015-05-11 | D |  |  | 2015-06-10 | E |  |  | 2015-06-12 | E |  |  | 2015-06-25 | F |  |  | 2015-07-22 | F |  |  | 2015-08-18 | G |  |  |  | 80% |  |  | 80%
2.4 | S | General arrangement drawings of SCR system components | KR1020 | 00HSJ | &MLH020 | 217110 | 445329711 | FA | - | 2014-09-26 | 2014-09-26 | A |  |  | 2014-12-22 | B |  |  | 2015-04-24 | C |  |  | 2015-04-27 | D |  |  | 2015-08-18 | E | [23 empty] | 80% |  |  | 80%
2.5 | S | Piping layout for SCR system | KR1020 | 00HSJ | &MLH020 | 217160 | 445330625 | FA | - | 2014-10-30 | 2014-10-30 | A |  |  | 2014-11-20 | B |  |  | 2015-04-22 | C | [31 empty] | 80% |  |  | 80%
2.6 |  | Piping layout detail drawing for SCR system | KR1020 | 00HSJ | &BBC020 | 141001 |  | FI | - | 2014-12-19 | [41 empty] | 0% |  |  | 0%
2.7 |  | Nozzle arrangement drawing for SCR system | KR1020 | 00HSJ | &BBC020 | 141002 |  | FA | - | 2014-10-15 | 2014-10-15 | A |  |  | 2014-11-20 | B |  |  | 2014-12-10 | C |  |  | 2014-12-22 | D | [26 empty] | added for internal design schedule | 80% |  |  | 80%
2.8 |  | Catalyst frame and gas sealing arrangement drawing for SCR system | KR1020 | 00HSJ | &BBC020 | 141003 |  | FA | - | 2014-10-15 | 2014-10-15 | A |  |  | 2014-11-28 | B |  |  | 2015-03-19 | C |  |  | 2015-04-24 | D |  |  | 2015-05-07 | E |  |  | 15-07-09 | F |  |  | 15-07-23 | G |  |  | 15-08-04 | H |  |  | 15-08-13 | I | [7 empty] | 80% |  |  | 80%
2.9 |  | Catalyst frame and gas sealing detail drawing for SCR system | KR1020 | 00HSJ | &BBC020 | 141004 |  | FI | - | 2014-12-19 | [41 empty] | 0% |  |  | 0%
2.1 |  | AIG arrangement drawing for SCR system | KR1020 | 00HSJ | &BBC020 | 141005 |  | FA | - | 2014-10-15 | 2014-10-15 | A |  |  | 2014-11-20 | B |  |  | 2015-02-25 | C |  |  | 2015-03-06 | D |  |  | 2015-04-28 | E |  |  | 2015-05-14 | F |  |  | 2015-07-13 | F |  |  | 15-07-23 | G |  |  | 2015-08-05 | G | [7 empty] | 80% |  |  | 80%
2.11 |  | AIG detail drawing for SCR system | KR1020 | 00HSJ | &BBC020 | 141006 |  | FI | - | 2015-01-10 | 2015-07-13 | A |  |  | 2015-08-05 | B | [35 empty] | 70% |  |  | 70%
2.12 |  | Vaporizer arrangement drawing for SCR system | KR1020 | 00HSJ | &BBC020 | 141007 |  | FA | - | 2014-10-15 | 2014-10-15 | A |  |  | 2014-04-22 | B |  |  | 2015-05-08 | C |  |  | 2015-06-02 | D | [27 empty] | 80% |  |  | 80%
2.13 |  | Vaporizer detail drawing for SCR system | KR1020 | 00HSJ | &BBC020 | 141008 |  | FI | - | 2015-01-10 | [41 empty] | 0% |  |  | 0%
2.14 |  | AFCU arrangement drawing for SCR system | KR1020 | 00HSJ | &BBC020 | 141009 |  | FA | - | 2014-11-15 | 2014-11-17 | A |  |  | 2015-01-21 | B |  |  | 2015-03-09 | C |  |  | 2015-03-30 | D |  |  | 2015-05-08 | E | [23 empty] | 80% |  |  | 80%
2.15 |  | AFCU detail drawing for SCR system | KR1020 | 00HSJ | &BBC020 | 141010 |  | FI | - | 2015-01-25 | [41 empty] | 0% |  |  | 0%
2.16 |  | Manifold arrangement drawing for SCR system | KR1020 | 00HSJ | &BBC020 | 141011 |  | FA | - | 2014-10-15 | 2014-10-15 | A |  |  | 2014-04-22 | B |  |  | 2015-05-11 | C |  |  | 2015-06-02 | D | [27 empty] | 80% |  |  | 80%
2.17 |  | Manifold detail drawing for SCR system | KR1020 | 00HSJ | &BBC020 | 141012 |  | FI | - | 2015-01-25 | 2015-04-30 | A | [39 empty] | 80% |  |  | 80%
2.18 |  | Outer connection pipe arrangement drawing for SCR system | KR1020 | 00HSJ | &BBC020 | 141013 |  | FA | - | 2014-10-15 | 2014-10-15 | A |  |  | 2014-11-20 | B |  |  | 2014-12-22 | C |  |  | 2015-04-24 | D |  |  | 2015-05-11 | E | [23 empty] | 80% |  |  | 80%
2.19 |  | Outer connection pipe detail for SCR system | KR1020 | 00HSJ | &BBC020 | 141014 |  | FI | - | 2015-01-25 | [41 empty] | 0% |  |  | 0%
2.2 |  | Expansion joint layout drawing for SCR system | KR1020 | 00HSJ | &BBC020 | 141015 |  | FA | - | 2014-12-15 | 2015-01-23 | A |  |  | 2015-03-17 | B |  |  | 2015-06-24 | C | [31 empty] | 80% |  |  | 80%
2.21 |  | Ammonia Injection Nozzle layout drawing for SCR system | KR1020 | 00HSJ | &BBC020 | 141016 |  | FA | - | 2015-03-30 | 2015-03-30 | A |  |  | 2015-07-23 | B | [35 empty] | 80% |  |  | 80%
2.22 |  | Damper layout drawing for SCR system | KR1020 | 00HSJ | &BBC020 | 141017 |  | FA | - | 2014-12-15 | 2015-01-23 | A |  |  | 2016-06-22 | B | [35 empty] | 80% |  |  | 80%
2.23 |  | ISO drawing for SCR system (if required) | KR1020 | 00HSJ | &BBC020 | 141018 |  | FI | - | - | 2015-06-19 | A | [39 empty] | 0% |  |  | 0%
3 |  | Electrical and I&C
3.1 | S | Functional diagrams SCR system | KR1020 | 00HSJ | &EFF010 | 217191 | 445330670 | FA | - | 2014-11-17 | 2014-11-17 | A |  |  | 15-07-09 | B | [35 empty] | 80% |  |  | 80%
3.2 | S | Arrangement of the electrical components for SCR system | KR1020 | 00HSJ | &ELH020 | 217192 | 445330571 | FA | - | 2014-10-15 | 2014-10-15 | A |  |  | 2014-10-29 | B |  |  | 2015-04-07 | C |  |  | 2015-04-27 | D |  |  | 2015-05-04 | E |  |  | 2015-05-11 | F |  |  | 2015-05-15 | G |  |  | 2015-07-02 | H | [11 empty] | 80% |  |  | 80%
3.3 | S | Single line diagram for SCR system | KR1020 | 00HSJ | &EFA010 | 217193 | 445330588 | FA | - | 2014-10-15 | 2014-10-15 | A |  |  | 2014-10-31 | B |  |  | 2014-12-09 | C |  |  | 2015-03-23 | D |  |  | 2015-05-15 | E |  |  | 2015-07-02 | F | [19 empty] | 80% |  |  | 80%
3.4 | S | Circuit diagrams for SCR system | KR1020 | 00HSJ | &EFS010 | 217194 | 445330595 | FA | - | 2014-10-15 | 2014-10-15 | A |  |  | 2014-11-28 | B |  |  | 2014-12-09 | C |  |  | 2014-12-11 | D |  |  | 2015-03-25 | E |  |  | 2015-05-22 | F | [19 empty] | 80% |  |  | 80%
3.5 | S | List of setting values for SCR system | KR1020 | 00HSJ | &MWA010 | 217195 | 445330601 | FA | - | 2015-05-03 | 2015-04-23 | A |  |  | 2015-05-19 | B |  |  | 2015-05-20 | C |  |  | 2015-07-22 | D | [27 empty] | 80% |  |  | 80%
3.6 | S | Wiring connection diagrams of I&C and electrical equipment for SCR system | [8 empty] | 2015-03-23 | A | [39 empty] | 80% |  |  | 80%
3.6.1 | S | Wiring connection diagrams for I&C of SCR system and cabling termination point | KR1020 | 00HSJ | &EMA020 | 217196 | 445330618 | FA | 2014-11-28 | 2015-05-03 | 2015-03-23 | A |  |  | 2015-06-09 | B |  |  | 2015-06-22 | C |  |  | 2015-07-06 | D | [26 empty] | In order to calculate cable and make connection diagram, preliminary document shall be submitted. | 80% |  |  | 80%
3.6.2 | S | Wiring connection diagrams for electrical equipment of SCR system and cabling termination point | KR1020 | 00HSJ | &EMA020 | 217197 | 445330656 | FA | - | 2015-05-03 | 2015-03-10 | A |  |  | 2015-06-09 | B |  |  | 2015-06-22 | C |  |  | 2015-07-06 | D | [27 empty] | 80% |  |  | 80%
3.7 |  | Electric load list for SCR System | KR1020 | 00HSJ | &BBC030 | 141101 |  | FA | - | 2014-10-08 | 2014-10-08 | A |  |  | 2014-10-21 | B |  |  | 2014-12-09 | C |  |  | 2015-03-11 | D | [26 empty] | for internal document schedule | 80% |  |  | 80%
3.8 |  | DCS I/O list for SCR System | KR1020 | 00HSJ | &BBC030 | 141102 |  | FA | - | 2014-10-15 | 2014-10-14 | A |  |  | 2015-04-23 | B |  |  | 2015-05-22 | C |  |  | 2015-07-22 | C | [27 empty] | 80% |  |  | 80%
3.9 |  | Instrument list for SCR system | KR1020 | 00HSJ | &BBC030 | 141103 |  | FA | - | 2014-12-21 | 2014-12-21 | A |  |  | 2015-03-20 | B |  |  | 2015-04-09 | C |  |  | 2015-05-04 | D |  |  | 2015-05-20 | E |  |  | 2015-06-24 | F |  |  | 2015-07-02 | G | [15 empty] | 80% |  |  | 80%
3.1 |  | Control logic diagram for SCR system | KR1020 | 00HSJ | &BBC030 | 141104 |  | FA | - | 2015-04-17 | 2014-12-09 | A | [39 empty] | 80% |  |  | 80%
3.11 |  | Control loop diagram for SCR system | KR1020 | 00HSJ | &BBC030 | 141105 |  | FA | - | 2015-04-17 | 2014-12-09 | A | [39 empty] | 80% |  |  | 80%
3.12 |  | Instrument installation drawing(hook-up) for SCR system | KR1020 | 00HSJ | &BBC030 | 141106 |  | FA | - | 2015-01-16 | 2015-06-09 | A |  |  | 2015-06-25 | B |  |  | 2015-07-22 | C | [31 empty] | 70% |  |  | 70%
3.13 |  | Panel and junction box drawing for SCR system | KR1020 | 00HSJ | &BBC030 | 141107 |  | FA | - | 2015-02-13 | 2015-02-13 | A |  |  | 2015-03-27 | B |  |  | 2015-05-22 | C |  |  | 2015-06-11 | D |  |  | 2015-07-06 | E | [23 empty] | 80% |  |  | 80%
3.14 |  | LCD graphic drawing for SCR system | KR1020 | 00HSJ | &BBC030 | 141108 |  | FA | - | 2015-04-17 | 2015-05-15 | A |  |  | 2015-06-22 | B | [35 empty] | 80% |  |  | 80%
3.15 |  | Conduit & cable tray layout drawing for SCR system | KR1020 | 00HSJ | &BBC030 | 141109 |  | FA | - | 2015-01-23 | 2014-12-26 | 0 |  |  | 2015-05-04 | A |  |  | 2015-05-22 | B | [31 empty] | 80% |  |  | 80%
3.16 |  | Function valve list for SCR system | KR1020 | 00HSJ | &BBC030 | 141110 |  | FA | - | 2015-12-21 | 2014-12-21 | A |  |  | 2015-03-20 | B |  |  | 2015-07-07 | C | [31 empty] | 80% |  |  | 80%
3.17 |  | Cable schedule for SCR system | KR1020 | 00HSJ | &BBC030 | 141111 |  | FA | - | 2015-02-27 | 2015-03-11 | A |  |  | 2015-06-09 | B |  |  | 2015-06-22 | C | [31 empty] | 80% |  |  | 80%
3.17 |  | Blackbox Interface Diagram for SCR system | KR1020 | 00HSJ | &BBC030 | 141112 |  | FI | - | 2014-10-15 | 2014-10-15 | A |  |  | 2015-04-09 | B |  |  | 2015-05-07 | C |  |  | 2015-06-05 | D |  |  | 2015-06-10 | E |  |  | 15-07-09 | F | [18 empty] | additional document by BBC | 80% |  |  | 80%
3.18 |  | Instrument Data Sheet for SCR system | KR1020 | 00HSJ | &BBC030 | 141113 |  | FA | - | 2015-05-20 | 2015-05-20 | A |  |  | 2015-06-24 | B |  |  | 2015-07-02 | C | [31 empty] | 80%
3.19 |  | Functional Valve Data Sheet for SCR system | KR1020 | 00HSJ | &BBC030 | 141114 |  | FA | - | 2015-05-15 | 2015-05-15 | A |  |  | 2015-07-07 | B
3.2 |  | Instrument Location Drawing for SCR system | KR1020 | 00HSJ | &BBC030 | 141115 |  | FA | - | 2015-05-19 | 2015-05-19 | A |  |  | 2015-07-20 | B
3.21 |  | Analyzer Data Sheet & Drawing | KR1020 | 00HSJ | &BBC030 | 141116 |  | FA | - | - | 2015-06-23 | A
4 |  | Quality Documents
4.1 | S | Inspection and Test Plan for Shop (SCR) | KR1020 | 00HSJ | &MDC080 | 217410 | 445329476 | FA | - | 2014-09-26 | 2014-09-26 | A |  |  | 2014-10-24 | B |  |  | 2014-11-28 | C | [31 empty] | 80% |  |  | 80%
4.2 | S | NCRs (SCR) | KR1020 | 00HSJ | &AQA020 | 217420 | 445330632 | FI | - | latest 1 day after recognition of individual NCR | [41 empty] | 80% |  |  | 80%
4.3 | S | Quality Document Package (SCR) | KR1020 | 00HSJ | &CQC040 | 217430 | 445330649 | FI | - | at shipment date | [41 empty] | 0% |  |  | 0%
4.4 | S | Quality Assurance Procedure & Manual for SCR | KR1020 | 00HSJ | &AQA010 | 217440 | 445329735 | FA | - | 2014-09-26 | 2014-09-26 | A | 2014-10-20 |  | 2014-10-31 | B | [35 empty] | 80% |  |  | 80%
4.5 | S | Inspection and test Procedures for SCR | KR1020 | 00HSJ | &MDC080 | 217450 | 445329742 | FA | - | 2014-09-26 | 2014-09-26 | A | 2014-10-20 |  | 2014-10-24 | B |  |  | 2014-11-28 | C |  |  | 2015-04-10 | -04 | [27 empty] | 80% |  |  | 80%
4.6 | S | Non-destructive examination Procedure for SCR | KR1020 | 00HSJ | &MDC080 | 217460 | 445329759 | FA | - | 2014-09-26 | 2014-09-26 | A | 2014-10-20 |  | 2014-10-24 | B |  |  | 2014-11-28 | C |  |  | 2015-06-02 | -04 |  |  | 2015-07-03 | -05 | [23 empty] | 80% |  |  | 80%
4.7 | S | WPS/PQR for SCR | KR1020 | 00HSJ | &MQC070 | 217470 | 445329766 | FA | - | 2014-09-26 | 2014-09-26 | A | 2014-10-20 |  | 2014-10-24 | B |  |  | 2014-11-28 | C |  |  | 2015-06-10 | -04 | [27 empty] | 80% |  |  | 80%
4.8 | S | Repair welding procedure for SCR | KR1020 | 00HSJ | &MDC050 | 217480 | 445329773 | FA | - | 2014-09-26 | 2014-09-26 | A | 2014-10-20 |  | 2014-10-24 | B |  |  | 2014-12-19 | C |  |  | 2015-06-02 | -04 |  |  | 2015-06-16 | -05 | [23 empty] | 80% |  |  | 80%
4.9 | S | Painting Procedure for SCR | KR1020 | 00HSJ | &ABZ010 | 217490 | 445329780 | FA | - | 2014-09-26 | 2014-09-26 | A | 2014-10-20 |  | 2014-10-24 | B | [35 empty] | 80% |  |  | 80%
4.1 | S | Shipping, handling and storage procedures for SCR | KR1020 | 00HSJ | &ADZ010 | 217491 | 445329797 | FA | - | 2014-09-26 | 2014-09-26 | A | 2014-10-20 | [38 empty] | 80% |  |  | 80%
5 |  | Transportation
5.1 | S | shipping documentation | KR1020 | 00UHA | &ABF020 | 217520 | 445330663 | FI | - | 1 week before shipment | [41 empty] | 0% |  |  | 0%
5.2 | S | Quality Release Note for SCR | KR1020 | 00HSJ | &MQC050 | 217530 | 445330717 | FI | - | at shipment | [41 empty] | 0% |  |  | 0%
[52 empty] | 67.07% | #DIV/0! | #DIV/0! | 66.91%

## 5. Submittal Document List
WAKAYAMA Document Control List
Doc. No.: -
Package Name : WAKAYAMA HRSG | [7 empty] | P.O. | 2024-04-05 | [40 empty] | Rev. No. : -
Vendor Name : BHI. CO.,LTD | [8 empty] | First | Final | [39 empty] | Dated : -
DOCUMENT NUMBER (CODE) |  |  |  |  | DOC NO. | Title | Purpose | Dept. | PLAN (week, from P.O) | PLAN (week, from P.O) | 수정날짜 | Remark | Final Issue Date (Plan) | L.D | 1st | [5 empty] | 2nd | [5 empty] | 3rd | [5 empty] | 4th | [5 empty] | 5th | [5 empty] | AS-BUILT |  |  |  |  | Remark | 내부 관리용
PJT No |  | Category |  | Serial No | [10 empty] | Submit |  |  | Return |  |  | Submit |  |  | Return |  |  | Submit |  |  | Return |  |  | Submit |  |  | Return |  |  | Submit |  |  | Return |  |  | Submit |  | Return |  |  |  | Submit |  | Return
[15 empty] | Date | REV | Transmittal No. | Date | Transmittal No. | Status | Date | REV | Transmittal No. | Date | Transmittal No. | Status | Date | REV | Transmittal No. | Date | Transmittal No. | Status | Date | REV | Transmittal No. | Date | Transmittal No. | Status | Date | REV | Transmittal No. | Date | Transmittal No. | Status | Date | Rev. | Date | Transmittal No. | Status |  | Date | REV | Date | Status
GENERAL / SCHEDULE
SCR (Mechanical)
23HG011 | - | SCR | - | 001 |  | P&ID FOR SCR | FA |  | 1 | 2024-04-12 | [10 empty] | 2024-04-15 | 1 |  | 2024-06-05 |  | R | 2024-06-17 | 2 |  |  |  |  | 2024.08.30 | 3 | [16 empty] | #REF! | #REF! | #REF! | #REF! | HRSG SCR GENERAL ARRANGEMENT DRAWING 폴더
23HG011 | - | SCR | - | 002 |  | EQUIPMENT FOUNDATION LOADING DATA & DRAWING FOR SCR | FA |  | 1 | 2024-04-12 |  |  |  |  | 2024-04-15 | 0 |  |  |  |  | 2024-06-18 | 1 |  |  |  |  | 2024-07-09 | 2 |  |  |  |  | 2024.07.16 | 1 |  |  |  |  | 2024.10.22 | 2 | [10 empty] | #REF! | #REF! | #REF! | #REF! | HRSG SYSTEM & AUXILIARY EQUIPMENTS FOUNDATION DRAWINGS (FOOTPRINT) 폴더
23HG011 | - | SCR | - | 003 |  | AIG ARRAGEMENT DRAWING | FA |  | 2 | 2024-04-19 |  |  |  |  | 2024-05-08 | 0 |  |  |  |  | 2024-06-26 | 1 |  |  |  |  | 2025-06-24 | 2 | [22 empty] | #REF! | #REF! | #REF! | #REF! | HRSG SCR GENERAL ARRANGEMENT DRAWING 폴더
23HG011 | - | SCR | - | 004 |  | CATALYST BLOCK DRAWING | FA |  | 2 | 2024-04-19 | 2024-08-15 |  |  |  | 2024-08-20 | 0 |  |  |  |  | 2024-10-14 | 1 |  |  |  |  | 2025-05-12 | 2 | [22 empty] | #REF! | #REF! | #REF! | #REF!
23HG011 | - | SCR | - | 005 |  | CATALYST SUPPORT STRUCTURE & SEALING ARRAGEMENT DRAWING | FA |  | 6 | 2024-05-17 | 2024-07-31 |  |  |  | 2024-08-28 | 0 |  |  |  |  | 2024-10-11 | 1 |  |  |  |  | 2025-05-12 | 2 |  |  |  |  | 2025-06-17 | 3 | [16 empty] | #REF! | #REF! | #REF! | #REF! | HRSG SCR GENERAL ARRANGEMENT DRAWING 폴더
23HG011 | - | SCR | - | 006 |  | AMMONIA DISTRIBUTION HEADER DRAWING | FA |  | 4 | 2024-05-03 |  |  |  |  | 2024-06-10 | 0 | [34 empty] | #REF! | #REF! | #REF! | #REF! | HRSG SCR SYSTEM MECHANICAL & PIPING DATASHEETS、SPECIFICATION & DRAWINGS 폴더
23HG011 | - | SCR | - | 007 |  | DILUTION AIR FAN DATA SHEET AND DRAWING | FA |  | 6 | 2024-05-17 | 2024-07-20 |  |  |  | 2024-07-18 | 0 |  |  |  |  | 2025-03-18 | 1 | [28 empty] | #REF! | #REF! | #REF! | #REF! | HRSG SCR SYSTEM MECHANICAL & PIPING DATASHEETS、SPECIFICATION & DRAWINGS 폴더
23HG011 | - | SCR | - | 008 |  | SCR SKID ARRANGEMENT | FA |  | 1 | 2024-04-12 |  |  |  |  | 2024-04-15 | 0 |  |  |  |  | 2024-12-18 | 1 | [28 empty] | #REF! | #REF! | #REF! | #REF! | HRSG SCR SYSTEM MECHANICAL & PIPING DATASHEETS、SPECIFICATION & DRAWINGS 폴더
23HG011 | - | SCR | - | 009 |  | AMMONIA & AIR MIXER DRAWING FOR HRSG SCR | FA |  | 6 | 2024-05-17 | 2024-08-30 |  |  |  | 2024-07-17 | 0 |  |  |  |  | 2025-06-23 | 1 | [28 empty] | #REF! | #REF! | #REF! | #REF! | HRSG SCR SYSTEM MECHANICAL & PIPING DATASHEETS、SPECIFICATION & DRAWINGS 폴더
23HG011 | - | SCR | - | 013 |  | SCR EQUIPMENT SIZING CALCULATION | FA |  | 4 | 2024-05-03 | 2024-07-05 |  |  |  | 2024-08-30 | 0 | [34 empty] | #REF! | #REF! | #REF! | #REF! | HRSG/AMMONIA SYSTEM SIZING CALCULATION FOR FAN 폴더
23HG011 | - | SCR | - | 014 |  | CFD REPORT FOR HRSG SCR | FI |  | 16 | 2024-07-26 |  |  |  |  | 2024-07-26 | 0
23HG011 | - | SCR | - | 015 |  | SCR System Description | FA |  | 2 | 2024-04-19 |  |  |  |  | 2024-04-26 | 0 |  |  |  |  | 2024-11-19 | 1
23HG011 | - | SCR | - | 016 |  | SCR Performance Calculation | FI |  | 2 | 2024-04-19 | [10 empty] | 2024-04-19 | 1 |  |  |  |  | 2024-11-20 | 2 | [22 empty] | #REF! | #REF! | #REF! | #REF!
23HG011 | - | SCR | - | 017 |  | SCR Data sheet | FA |  | 2 | 2024-04-19 | [10 empty] | 2024-04-19 | 1 |  |  |  |  | 2024-11-14 | 2 | [22 empty] | #REF! | #REF! | #REF! | #REF!
23HG011 | - | SCR | - | 018 |  | Flow Diagram for SCR | FA |  | 2 | 2024-04-19 | 2024-06-28 |  |  |  | 2024-09-20 | 0 | [34 empty] | #REF! | #REF! | #REF! | #REF!
SCR (Piping)
23HG011 | - | SCR | - | 019 |  | VALVE LIST FOR SCR & AMMONIA SYSTEM | FA |  | 7 | 2024-05-24 | 2024-07-05 |  |  |  | 2024-08-02 | 0 |  |  |  |  | 2025-04-18 | 1 | [28 empty] | #REF! | #REF! | #REF! | #REF! | HRSG SCR SYSTEM MECHANICAL & PIPING DATASHEETS、SPECIFICATION & DRAWINGS (Note: SCR system includes Catalyst steel structural frame housing and modules)
23HG011 | - | SCR | - | 020 |  | LINE LIST FOR SCR & AMMONIA SYSTEM | FA |  | 7 | 2024-05-24 | 2024-07-05 |  |  |  | 2024-08-30 | 0 |  |  |  |  | 2025-04-18 | 1 | [28 empty] | #REF! | #REF! | #REF! | #REF! | HRSG SCR SYSTEM MECHANICAL & PIPING DATASHEETS、SPECIFICATION & DRAWINGS 폴더
23HG011 | - | SCR | - | 021 |  | PIPING ARRANGEMENT DRAWING FOR SCR & AMMONIA SYSTEM | FA |  | 11 | 2024-06-21 | 2024-12-30 |  |  |  | 2024-08-26 | 0 | [34 empty] | #REF! | #REF! | #REF! | #REF! | HRSG AMMONIA SYSTEM MECHANICAL & PIPING DATASHEETS、SPECIFICATION & DRAWINGS
23HG011 | - | SCR | - | 022 |  | PIPING SUPPORT DRAWING FOR SCR & AMMONIA SYSTEM | FA |  | 15 | 2024-07-19 | 2025-02-15 |  |  |  | 2024-10-11 | 0 | [34 empty] | #REF! | #REF! | #REF! | #REF! | HRSG AMMONIA SYSTEM MECHANICAL & PIPING DATASHEETS、SPECIFICATION & DRAWINGS
23HG011 | - | SCR | - | 023 |  | ISO DRAWING FOR SCR & AMMONIA SYSTEM | FA |  | 15 | 2024-07-19 | 2025-01-30 |  |  |  | 2024-09-23 | 0 | [34 empty] | #REF! | #REF! | #REF! | #REF! | HRSG AMMONIA SYSTEM MECHANICAL & PIPING DATASHEETS、SPECIFICATION & DRAWINGS
23HG011 | - | SCR | - | 024 |  | FUNCTIONAL VALVE LIST AND DATA SHEET FOR SCR & AMMONIA SYSTEM | FA |  | 11 | 2024-06-21 | 2024-12-30 |  |  |  | 2025-05-09 | 0 | [34 empty] | #REF! | #REF! | #REF! | #REF! | HRSG SCR SYSTEM MECHANICAL & PIPING DATASHEETS、SPECIFICATION & DRAWINGS 폴더
SCR (I&C)
23HG011 | - | SCR | - | 026 |  | INSTRUMENT LIST FOR SCR | FA |  | 4 | 2024-05-03 | 2024-07-05 |  |  |  | 2025-01-10 | 0 |  |  |  |  | 2025-02-25 | 1 |  |  |  |  | 2025-05-27 | 2 | [22 empty] | #REF! | #REF! | #REF! | #REF! | HRSG SCR SYSTEM INSTRUMENT DATASHEETS、SPECIFICATIONS & DRAWINGS 폴더
23HG011 | - | SCR | - | 027 |  | DCS I/O LIST FOR SCR | FA |  | 11 | 2024-06-21 | 2024-08-09 |  |  |  | 2024-08-16 | 0 |  |  |  |  | 2025-05-23 | 1 | [28 empty] | #REF! | #REF! | #REF! | #REF! | HRSG SCR SYSTEM INSTRUMENT DATASHEETS、SPECIFICATIONS & DRAWINGS 폴더
23HG011 | - | SCR | - | 028 |  | CABLE LIST & SCHEDULE FOR SCR | FA |  | 19 | 2024-08-16 | 2024-09-15 |  |  |  | 2024-12-12 | 0 | [38 empty] | HRSG SCR SYSTEM ELECTRICAL DATASHEETS、SPECIFICATIONS & DRAWINGS
23HG011 | - | SCR | - | 029 |  | CABLE INTERCONNECTION WIRING DIAGRAM FOR SCR | FA |  | 19 | 2024-08-16 | 2024-09-15 |  |  |  | 2024-08-16 | 0 |  |  |  |  | 2025-05-23 | 1 | [28 empty] | #REF! | #REF! | #REF! | #REF! | HRSG SCR SYSTEM ELECTRICAL DATASHEETS、SPECIFICATIONS & DRAWINGS
23HG011 | - | SCR | - | 031 |  | PANEL & JUNCTION BOX DRAWING FOR SCR | FA |  | 21 | 2024-08-30 | 2024-10-30 |  |  |  | 2024-10-25 | 0 | [34 empty] | #REF! | #REF! | #REF! | #REF! | HRSG SCR SYSTEM ELECTRICAL DATASHEETS、SPECIFICATIONS & DRAWINGS
23HG011 | - | SCR | - | 032 |  | INSTRUMENT INSTALLATION DRAWING FOR SCR | FA |  | 21 | 2024-08-30 | 2025-01-15 | instrument datasheet 접수 후 2주 |  |  | 2025-07-04 | 0 | [34 empty] | #REF! | #REF! | #REF! | #REF! | HRSG SCR SYSTEM INSTRUMENT DATASHEETS、SPECIFICATIONS & DRAWINGS
23HG011 | - | SCR | - | 033 |  | ANALYZER DATA SHEET & DRAWING FOR SCR | FA |  | 23 | 2024-09-13 | 2024-08-30 | [39 empty] | #REF! | #REF! | #REF! | #REF! | HRSG SCR SYSTEM INSTRUMENT DATASHEETS、SPECIFICATIONS & DRAWINGS 폴더
23HG011 | - | SCR | - | 034 |  | SYSTEM CONFIGURATION FOR SCR | FA |  | 19 | 2024-08-16 | 2024-08-16 |  |  |  | 2024-10-23 | 0 |  |  |  |  | 2024-12-10 | 1 | [28 empty] | #REF! | #REF! | #REF! | #REF!
23HG011 | - | SCR | - | 036 |  | INSTRUMENT DATA SHEET & DRAWING FOR SCR | FA |  | 23 | 2024-09-13 | 2024-12-30 |  |  |  | 2025-05-30 | 0 | [34 empty] | #REF! | #REF! | #REF! | #REF!
23HG012 | - | SCR | - | 037 |  | ERECTION PROCEDURE FOR SCR | FA |  | 11 | 2024-06-21 | 2025-06-01 |  |  |  | 2025-02-28 | 0
23HG013 | - | SCR | - | 038 |  | COMMISSIONING PROCEDURE FOR SCR | FI |  | 39 | 2025-01-03 | 2025-06-01 |  |  |  | 2025-04-04 | 0
23HG014 | - | SCR | - | 039 |  | PERFORMANCE TEST PROCEDURE FOR SCR | FA |  | 39 | 2025-01-03 | 2025-06-01 |  |  |  | 2025-05-23 | 0
23HG015 | - | SCR | - | 040 |  | OPERATION AND MAINTENANCE MANUAL FOR SCR | FI |  | 46 | 2025-02-21 | 2025-07-15 |  |  |  | 2025-06-09 | 0
23HG017 | - | SCR | - | 041 |  | Control Logic Diagram for SCR | FA |  | 13 | 2024-07-05 | 2024-08-30 | SET POINT LIST 접수 후 2주 |  |  | 2024-10-23 | 0 |  |  |  |  | 2024-12-13 | 1
[6 empty] | Control Loop Diagram for SCR | FA |  | 13 | 2024-07-05 | 2024-08-30 | SET POINT LIST 접수 후 2주 |  |  | 2024-10-22 | 0
[6 empty] | Instrument Location Drawing For SCR | FA |  | 15 | 2024-07-19 | 2025-01-15 | piping arrangement 접수 후 2주 |  |  | 2024-10-24 | 0
23HG011 | - | SCR | - | 042 |  | Control Loop Diagram for SCR | FA |  | 13 | 2024-07-05 | 2024-08-30 | SET POINT LIST 접수 후 2주 |  |  | 2024-10-22 | 0 |  |  |  |  | 2024-12-13 | 1
23HG011 | - | SCR | - | 043 |  | Instrument Location Drawing For SCR | FA |  | 15 | 2024-07-19 | 2025-01-15 | piping arrangement 접수 후 2주 |  |  | 2024-10-24 | 0
23HG011 | - | SCR | - | 044 |  | Cable Specification for SCR | FA |  | 13 | 2024-07-05 | - | 케이블 구매 업체가 정해진 후 접수 가능합니다. |  |  | 2024-11-29 | 0 | [34 empty] | #REF! | #REF! | #REF! | #REF!
Formulas:
Final = J3+[First]*7

## 6. Shipping Plan (hidden)
6. Shipping Plan | [12 empty] | 2025-08-30
No. | Item Name | Q'ty |  | Dimension (m) |  |  | CBM | Weight (ton) | Pre-assembly level | Delivery Date | CBM per Shipment |  |  | Remark
|  | Unit | Total | W | H | L |  |  |  |  | 1 | 2 | 3
[11 empty] | 2021-07-10 | 2021-12-18 | 2022-11-28
(To be later)
| Total | [5 empty] | 0 | 0 |  |  | 0 | 0 | 0
1 cbm 당 167kg

## 7. Change Order (hidden)
7. Change Order Status |  |  |  |  | 2025-08-30
Date | Rev. No. | Description | Amount change per revision | Total amount | Remark

## 8. ISSUE (hidden)
8. Issue |  |  | 2025-08-30
P.O Line NO. | Description | Issue